| Delegation Planning Worksheet |  | Greeters |  |  |
| --- | --- | --- | --- | --- |
| Description of Project |  |  | Delegated to |  |
| To Schedule, Organize, build the team and train greeters for each campus |  |  | Reach Up Team |  |
| Significance of project and relative priority to other projects |  |  |  |  |
| We have a nearly non-existent Greeter System at BOTH campuses. Statistics show that people make a decision to come back within the first 2 minutes – that makes the greeters vitally important. |  |  |  |  |
| Objectives/Results Expected |  |  | Completion Deadline |  |
| - To find more greeters as needed according to the schedule - To hold a greeter’s training 2 Times a year |  |  | November 30, 2008 |  |
| Resources Available (people, time, money, training, etc.) |  |  |  |  |
| Church Database – electronically or hard copy (see Alice for info) Church Bulletins, Fliers (See Martin Poole) to help build team Kelli Calderon for scheduling |  |  |  |  |
| Authority granted to complete Project (over resources, budget, etc.) |  |  |  |  |
| To build a team of greeters and to build a schedule for each campus. To schedule a training event for all greeters – even the “old” ones – before the “new” ones start greeting |  |  |  |  |
| Identification of parties to notify about delegation of authority (parties affected) |  |  |  |  |
| Reach Up Team, Pastor Roger, |  |  |  |  |
| Potential Obstacles and Solutions |  |  |  |  |
| - Can’t find enough people – see Roger for more ideas - People don’t know what to do – schedule a training - Greeters don’t show up – After two times, fire them and find someone new - Greeters spending time talking with each other and ignoring new people – talk, renew commitment, retrain, and move on to new people if needed.... |  |  |  |  |
| Ideas for Project |  |  |  |  |
| - Find out what greeters we already have - Evaluate if they are doing a good job or not - Ask new people to fill out the schedule (3 on East, 2-3 on West) |  |  |  |  |
| Checkpoints of Major Activity Completion |  |  | Target Dates |  |
| - Date Chosen for Training |  |  | By October 10, 2008 |  |
| - People asked to serve |  |  | By November 6, 2008 |  |
| - Training Conducted |  |  | By November 6, 2008 |  |
| - Schedule Completed |  |  | By November 10, 2008 |  |
| Communication Plan |  |  |  |  |
| Parties to Keep Informed | Method |  |  | Frequency |
| Roger | coach@theadventure.org |  |  | Weekly |
| Alice | alipiotr@aol.com |  |  | Weekly |

/tmp/in/input.doc